## Info
DAGσPERT steht für: Delphi Aufwandschätzung in Gruppen unter Berücksichtigung von σ (Standardabweichung) mit PERT (Program Evaluation and Review Technique). Die Version 2016_slim wurde gegenüber der Version 2016_full stark vereinfacht, um einen besseren Einstieg in die Verwendung zu ermöglichen.
Für dieses Schätzwerkzeug wurden ein Delphi Verfahren, PERT, Storypoints, T-Shirt Sizing und andere Schätzverfahren kombiniert.
Beachten Sie die dazugehörige Anleitung!
- Schätzung in Personenstunden und in abstrakten Sorypoints
- Integration von T-Shirt Sizing
Der Blattschutz ist aktiviert, damit Sie nicht unabsichtlich Formeln überschreiben können. Bereiche für Benutzereingaben sind freigegeben.
Copyright: CSS Computer-Systems-Support GmbH, Dipl.-Ing.(FH) Sven Schweiger 2007-2016.

## Spezifikation
Delphi Verfahren mit PERT - Unsicherheit ausdrückbar durch Schätzbereich: Breite, p(range) | [13 empty] | T-Shirt-Sizing
ID | Themes / Areas / Arbeitspakete Toplevel | Epics / User Stories / Arbeitspakete TopLevel | User Stories / Detail Level / Beschreibung | Optimistisch (Sp) | Wahrscheinlich (Sp) | Pessimistisch (Sp) | Dokumentation von Annahmen, Überlegungen, Risiken, Bedingungen und Diskussionsergebnissen aus dem Schätzmeeting | Erwartet nach PERT 1:4:1 (Sp) | Kalibrierter erwarteter Aufwand (Ph) | p(range) (5-100) | Divisor (0,25-6) | Standard- Abweichung (Ph) | Varianz | Aufwand (T-Shirt: XS-XXL) | Businesswert (T-Shirt: XS-XXL) | Nettobusiness- wert (T-Shirt: XS-XXL)
|  |  |  | 162.5 | 274.5 | 436 |  | 282.75 | 565.5 |  |  | 13.2696 | 176.0833
509 | A-SIA 2.0 | 508 Menubar | User can use File Menubar Menu | 1 | 2 | 3 | Siehe azure Devops | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
510 | A-SIA 2.0 | 508 Menubar | User can use Edit Menubar Menu | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
511 | A-SIA 2.0 | 508 Menubar | User can use View Menubar Menu | 0 | 1 | 2 |  | 1 | 2 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
513 | A-SIA 2.0\basic | 512 Highlevel Network Management | User wants to create Network (backend) | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
514 | A-SIA 2.0\basic | 512 Highlevel Network Management | User wants to open Network | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
515 | A-SIA 2.0\Mid | 512 Highlevel Network Management | User wants to Export their network | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | M | M
516 | A-SIA 2.0\Mid | 512 Highlevel Network Management | User wants to import a network | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | M | M
520 | A-SIA 2.0\basic | 517 Sidebar Network | User wants to change Network Name | 0.5 | 0.5 | 1 |  | 0.58333 | 1.1667 | 99.73 | 6 | 0.16667 | 0.027778 | S | S | S
521 | A-SIA 2.0\basic | 517 Sidebar Network | User wants to change Network Description | 0.5 | 0.5 | 1 |  | 0.58333 | 1.1667 | 99.73 | 6 | 0.16667 | 0.027778 | S | S | S
522 | A-SIA 2.0\Mid | 517 Sidebar Network | User wants to Anonymize Network Display | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | M | M
523 | A-SIA 2.0\basic | 517 Sidebar Network | User wants to access reporting | 0.5 | 0.5 | 1 |  | 0.58333 | 1.1667 | 99.73 | 6 | 0.16667 | 0.027778 | S | S | S
524 | A-SIA 2.0\basic | 517 Sidebar Network | User wants to delete network | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
525 | A-SIA 2.0\basic | 519 Sidebar Structure | User wants to have a hierarchical list of their network structure | 3 | 5 | 8 |  | 5.1667 | 10.3333 | 99.73 | 6 | 1.6667 | 2.7778 | M | S | XS
526 | A-SIA 2.0\basic | 519 Sidebar Structure | User wants to expand / collapse network structure | 3 | 5 | 8 |  | 5.1667 | 10.3333 | 99.73 | 6 | 1.6667 | 2.7778 | M | S | XS
527 | A-SIA 2.0\Mid | 519 Sidebar Structure | User wants to navigate to node via a structure entry | 3 | 5 | 8 |  | 5.1667 | 10.3333 | 99.73 | 6 | 1.6667 | 2.7778 | M | M | M
528 | A-SIA 2.0\basic | 519 Sidebar Structure | User wants to add a person through the structure tab | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | S | XS
529 | A-SIA 2.0\Large | 519 Sidebar Structure | User wants to add a group through the structure tab | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | L | L
531 | A-SIA 2.0\basic | 530 Sidebar | User wants to Navigate between Network / Structure / Inspector | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
532 | A-SIA 2.0\basic | 530 Sidebar | User wants to toggle Sidebar | 0.5 | 1 | 2 |  | 1.0833 | 2.1667 | 99.73 | 6 | 0.5 | 0.25 | S | S | S
533 | A-SIA 2.0\basic | 530 Sidebar | User wants to resize Sidebar | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
534 | A-SIA 2.0\basic | 518 Sidebar Inspector | User wants to access person data through inspector | 0.5 | 1 | 2 |  | 1.0833 | 2.1667 | 99.73 | 6 | 0.5 | 0.25 | S | S | S
535 | A-SIA 2.0\Large | 518 Sidebar Inspector | User wants to access group data through inspector | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | L | L
536 | A-SIA 2.0\basic | 518 Sidebar Inspector | User wants to access connection data through inspector | 0 | 1 | 2 |  | 1 | 2 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
540 | A-SIA 2.0\basic | 537 Inspector Person | User wants to change T(0) through slider in inspector | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
541 | A-SIA 2.0\basic | 537 Inspector Person | User wants to change person name through in inspector | 0.5 | 1 | 2 |  | 1.0833 | 2.1667 | 99.73 | 6 | 0.5 | 0.25 | S | S | S
542 | A-SIA 2.0\basic | 537 Inspector Person | User wants to change person echodämpfung / beharrlichkeit in inspector | 0.5 | 1 | 2 |  | 1.0833 | 2.1667 | 99.73 | 6 | 0.5 | 0.25 | S | S | S
543 | A-SIA 2.0\Mid | 537 Inspector Person | User wants to change person color randomly in inspector | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | M | M
544 | A-SIA 2.0\basic | 537 Inspector Person | User wants to see all adjourning connections to the selected Person in inspector | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
545 | A-SIA 2.0\basic | 537 Inspector Person | User wants to see all names and connecting connections between multiple persons in inspector | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
546 | A-SIA 2.0\Mid | 537 Inspector Person | User wants to see persons special role(s) in inspector | 3 | 5 | 8 |  | 5.1667 | 10.3333 | 99.73 | 6 | 1.6667 | 2.7778 | M | M | M
547 | A-SIA 2.0\basic | 537 Inspector Person | User wants to change person color through a color selector in inspector | 0 | 1 | 2 |  | 1 | 2 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
548 | A-SIA 2.0\basic | 539 Inspector Connection | User wants to change Connection direction through the click of a button | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
549 | A-SIA 2.0\basic | 539 Inspector Connection | User wants to change connection interval and offset via inspector | 0 | 1 | 2 |  | 1 | 2 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
550 | A-SIA 2.0\basic | 539 Inspector Connection | User wants to change connection Einfluss in inspector | 0 | 1 | 2 |  | 1 | 2 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
551 | A-SIA 2.0\Large | 538 Inspector Group | User wants to see averaged T(0), T(t), Echodämpfung, Beharrlichkeit of the group in the inspector | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | L | L
552 | A-SIA 2.0\Large | 538 Inspector Group | User wants to change color of the group in the inspector | 0 | 1 | 2 |  | 1 | 2 | 99.73 | 6 | 0.66667 | 0.44444 | S | L | L
553 | A-SIA 2.0\Large | 538 Inspector Group | User wants to see averaged connections of the group in the inspector | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | L | L
554 | A-SIA 2.0\Large | 538 Inspector Group | User wants to see containing nodes of the group in the inspector | 0.5 | 1 | 2 |  | 1.0833 | 2.1667 | 99.73 | 6 | 0.5 | 0.25 | S | L | L
555 | A-SIA 2.0\Large | 538 Inspector Group | User wants to see containing relations of the group in the inspector | 0.5 | 1 | 2 |  | 1.0833 | 2.1667 | 99.73 | 6 | 0.5 | 0.25 | S | L | L
556 | A-SIA 2.0\Large | 538 Inspector Group | User wants to see expand / collapse group through a button in the inspector | 0.5 | 1 | 2 |  | 1.0833 | 2.1667 | 99.73 | 6 | 0.5 | 0.25 | S | L | L
564 | A-SIA 2.0\basic | 561 Graph Editor Tools | User wants to reset simulation in graph editor | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
565 | A-SIA 2.0\basic | 561 Graph Editor Tools | User wants to skip to simulation frame in graph editor | 5 | 8 | 12 |  | 8.1667 | 16.3333 | 99.73 | 6 | 2.3333 | 5.4444 | L | S | XS
567 | A-SIA 2.0\basic | 561 Graph Editor Tools | User wants to navigate plus / minus one simulation frame in graph editor | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
569 | A-SIA 2.0\basic | 561 Graph Editor Tools | User wants to create person in graph editor | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | S | XS
571 | A-SIA 2.0\basic | 561 Graph Editor Tools | User wants to create connection in graph editor | 3 | 5 | 8 |  | 5.1667 | 10.3333 | 99.73 | 6 | 1.6667 | 2.7778 | M | S | XS
572 | A-SIA 2.0 | 561 Graph Editor Tools | User wants to automatically Arrange nodes in graph editor (TODO!) | 8 | 13 | 20 |  | 13.3333 | 26.6667 | 99.73 | 6 | 4 | 16 | L | M | S
573 | A-SIA 2.0\basic | 561 Graph Editor Tools | User wants to enable "connected selection filtering" in graph editor | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
574 | A-SIA 2.0\basic | 560 Graph Editor Navigation + Selection | User wants to zoom in graph editor | 3 | 5 | 8 |  | 5.1667 | 10.3333 | 99.73 | 6 | 1.6667 | 2.7778 | M | S | XS
575 | A-SIA 2.0\basic | 560 Graph Editor Navigation + Selection | User wants to pan in graph editor | 3 | 5 | 8 |  | 5.1667 | 10.3333 | 99.73 | 6 | 1.6667 | 2.7778 | M | S | XS
576 | A-SIA 2.0\basic | 560 Graph Editor Navigation + Selection | User wants to select Nodes / Connections in graph editor | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | S | XS
577 | A-SIA 2.0\basic | 560 Graph Editor Navigation + Selection | User wants to move Nodes in graph editor | 3 | 5 | 8 |  | 5.1667 | 10.3333 | 99.73 | 6 | 1.6667 | 2.7778 | M | S | XS
578 | A-SIA 2.0\Large | 560 Graph Editor Navigation + Selection | User wants to move Nodes into groups in graph editor | 5 | 8 | 12 |  | 8.1667 | 16.3333 | 99.73 | 6 | 2.3333 | 5.4444 | L | L | L
579 | A-SIA 2.0\Large | 560 Graph Editor Navigation + Selection | User wants to move Nodes out of groups in graph editor | 5 | 8 | 12 |  | 8.1667 | 16.3333 | 99.73 | 6 | 2.3333 | 5.4444 | L | L | L
580 | A-SIA 2.0\Large | 561 Graph Editor Tools | User wants to group / ungroup nodes in graph editor | 5 | 8 | 12 |  | 8.1667 | 16.3333 | 99.73 | 6 | 2.3333 | 5.4444 | L | L | L
581 | A-SIA 2.0\Large | 561 Graph Editor Tools | User wants to collapse / expand group nodes in graph editor | 13 | 20 | 30 |  | 20.5 | 41 | 99.73 | 6 | 5.6667 | 32.1111 | L | L | L
582 | A-SIA 2.0\basic | 560 Graph Editor Navigation + Selection | User wants to toggle graph editor | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
583 | A-SIA 2.0\basic | 560 Graph Editor Navigation + Selection | User wants to resize graph editor | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
585 | A-SIA 2.0\basic | 584 Simulation Diagram (Frage) | User wants to toggle Simulation Diagram | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
586 | A-SIA 2.0\basic | 584 Simulation Diagram (Frage) | User wants to resize Simulation Diagram | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
587 | A-SIA 2.0\basic | 584 Simulation Diagram (Frage) | User wants to see a legend for the Simulation Diagram | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
588 | A-SIA 2.0\basic | 584 Simulation Diagram (Frage) | User wants to expand / collapse groups through the legend within the Simulation Diagram (FRAGE) | 0.5 | 1 | 2 |  | 1.0833 | 2.1667 | 99.73 | 6 | 0.5 | 0.25 | S | S | S
589 | A-SIA 2.0\basic | 537 Inspector Person | User wants to change Avatar in inspector | 3 | 5 | 8 |  | 5.1667 | 10.3333 | 99.73 | 6 | 1.6667 | 2.7778 | M | S | XS
591 | A-SIA 2.0\basic | 584 Simulation Diagram (Frage) | User wants to see the simulation diagram | 3 | 5 | 8 |  | 5.1667 | 10.3333 | 99.73 | 6 | 1.6667 | 2.7778 | M | S | XS
592 | A-SIA 2.0\basic | 590 Graph Editor Display | User wants to see their person in the Graph editor | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | S | XS
593 | A-SIA 2.0\basic | 590 Graph Editor Display | User wants to see their connection in the Graph editor | 3 | 5 | 8 |  | 5.1667 | 10.3333 | 99.73 | 6 | 1.6667 | 2.7778 | M | S | XS
594 | A-SIA 2.0\Large | 590 Graph Editor Display | User wants to see their group in the Graph editor | 3 | 5 | 8 |  | 5.1667 | 10.3333 | 99.73 | 6 | 1.6667 | 2.7778 | M | L | L
595 | A-SIA 2.0\basic | 557 Database | Developer wants to have a basic graph database they can access | 3 | 5 | 8 |  | 5.1667 | 10.3333 | 99.73 | 6 | 1.6667 | 2.7778 | M | S | XS
597 | A-SIA 2.0\Mid | 596 Menubar Tools | User wants to access / change settings | 3 | 5 | 8 |  | 5.1667 | 10.3333 | 99.73 | 6 | 1.6667 | 2.7778 | M | M | M
598 | A-SIA 2.0\Mid | 596 Menubar Tools | User wants to undo / redo | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | M | M
600 | A-SIA 2.0\Mid | 599 User want to generate a report | User wants to have a network level report | [6 empty] | 99.73 | 6 |  |  |  | M
601 | A-SIA 2.0\Mid | 599 User want to generate a report | User wants to have a person level report | [6 empty] | 99.73 | 6 |  |  |  | M
602 | A-SIA 2.0\Large | 599 User want to generate a report | User wants to define template | [6 empty] | 99.73 | 6 |  |  |  | L
603 | A-SIA 2.0\Large | 599 User want to generate a report | User wants to define indicators (FRAGE) | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | L | L
604 | A-SIA 2.0\basic | 449 User wants to build their network from external data | User wants to generate network from survey data | [6 empty] | 99.73 | 6 |  |  |  | S
605 | A-SIA 2.0\basic | 449 User wants to build their network from external data | User wants to generate network from external tool | [6 empty] | 99.73 | 6 |  |  |  | S
607 | A-SIA 2.0\Mid | 537 Inspector Person | Developer wants to have an expandable calculation process of KPIs | [6 empty] | 99.73 | 6 |  |  |  | M
609 | A-SIA 2.0\Mid | 590 Graph Editor Display | User wants to see persons special role(s) in graph editor | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | M | M
610 | A-SIA 2.0\Large | 596 Menubar Tools | User can use common hotkeys | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | L | L
611 | A-SIA 2.0\basic | 557 Database | User wants to login (new Discussion) | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
621 | A-SIA 2.0\basic | 561 Graph Editor Tools | User can define Start Value of Nodes before/during simulation (NEW!) | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | S | XS
622 | A-SIA 2.0\Mid | 512 Highlevel Network Management | Save Network As (NEW!) | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | M | M
623 | A-SIA 2.0\Mid | 590 Graph Editor Display | User wants to see network specific metrics (NEW) | 2 | 3 | 5 |  | 3.1667 | 6.3333 | 99.73 | 6 | 1 | 1 | M | M | M
641 | A-SIA 2.0 | 561 Graph Editor Tools | User wants to simulate the network | 13 | 20 | 30 |  | 20.5 | 41 | 99.73 | 6 | 5.6667 | 32.1111 | L | L | L
649 | A-SIA 2.0 | 512 Highlevel Network Management | User wants to create Instance (backend) | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
650 | A-SIA 2.0 | 512 Highlevel Network Management | User wants to create project (backend) | 1 | 2 | 3 |  | 2 | 4 | 99.73 | 6 | 0.66667 | 0.44444 | S | S | S
666 | A-SIA 2.0 | 512 Highlevel Network Management | Developer wants to have prototype for instance>project>network hierarchy | 3 | 5 | 8 |  | 5.1667 | 10.3333 | 99.73 | 6 | 1.6667 | 2.7778 | M | M | M
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6
[10 empty] | 99.73 | 6

## Aufwandschätzung
Aufwandschätzung mit Zusagesicherheit (Konfidenzintervall)
Zusagesicherheit (% Konfidenz) | Aufwand (Personenstunden) | Aufwand (Personentage brutto) | Aufwand (Personenmonate brutto) | Aufwand (Personenjahre brutto)
2% | 538.9607 | 67.3701 | 3.3685 | 0.28071
10% | 548.5149 | 68.5644 | 3.4282 | 0.28568
16% | 552.2304 | 69.0288 | 3.4514 | 0.28762
20% | 554.3535 | 69.2942 | 3.4647 | 0.28873
25% | 556.6093 | 69.5762 | 3.4788 | 0.2899
30% | 558.5998 | 69.825 | 3.4912 | 0.29094
40% | 562.1826 | 70.2728 | 3.5136 | 0.2928
50% | 565.5 | 70.6875 | 3.5344 | 0.29453
60% | 568.8174 | 71.1022 | 3.5551 | 0.29626
70% | 572.4002 | 71.55 | 3.5775 | 0.29813
75% | 574.3907 | 71.7988 | 3.5899 | 0.29916
80% | 576.6465 | 72.0808 | 3.604 | 0.30034
84% | 578.7696 | 72.3462 | 3.6173 | 0.30144
90% | 582.4851 | 72.8106 | 3.6405 | 0.30338
98% | 592.0393 | 74.0049 | 3.7002 | 0.30835

## Angebotspreis
Angebotskalkulation
Parameter zur Angebotskalkulation
Stundensatz / Tagsatz
Stundensatz (EUR) 2) | 139
Stunden pro Tag 1) | 7.7
Tagsatzsatz (EUR) 2) | 1070.3
1) Umrechnungsfaktor "Stunden pro Tag" gilt für die Kostenberechnung, nicht für die Ressourcenberechnung!
2) Der Tagsatz bzw. Stundensatz ist bei dieser einfach Kalkulation ein Mischsatz für das Unternehmen bzw. das Projekt (inkl. Gemeinkosten, etc.)!
Vereinfachte Angebotskalkulation
| 25% Konfidenz | 50% Konfidenz | 75% Konfidenz | 98% Konfidenz
Gesamtaufwand (h) | 556.6093 | 565.5 | 574.3907 | 592.0393
Gesamtaufwand (Tage) | 72.2869 | 73.4416 | 74.5962 | 76.8882
Zusatzkosten 1 (EUR) | 0 | 0 | 0 | 0
Zusatzkosten 2 (EUR) | 0 | 0 | 0 | 0
Gesamtkosten (EUR) | 77368.6985 | 78604.5 | 79840.3015 | 82293.4598
Bemerkung zur Zusagesicherheit (% Konfidenz) | Nicht für Angebot geeignet - nur für den internen Gebrauch! | Bestenfalls bei strategischem Projekt als Angebot verwendbar. | Bei gut bekannten Projekttypen für Angebot einsetzbar. | Gut als Basis für Angebot einsetzbar.

## Einstellungen
Nettobusinesswert
Businesswert / Aufwand | XS | S | M | L | XL | XXL
XS | XS | S | M | L | XL | XXL
S | XS | S | M | L | XL | XXL
M | XS | XS | M | L | XL | XXL
L | XS | XS | S | L | XL | XXL
XL | XS | XS | S | M | XL | XXL
XXL | XS | XS | S | M | L | XXL
Nettobusinesswert | Umsetzung | Empfehlung bei Fixpreis
XS | nicht relevant | nicht relevant
S | kaum relevant | nicht relevant
M | möglich | nicht relevant
L | wichtig | COS / abnahmerelevant
XL | sehr wichtig | COS / abnahmerelevant
XXL | unbedingt | COS / abnahmerelevant
Kalibrierung Storypoints auf Personenstunden
Story Points | Kalibrierter Aufwand in Personen-stunden (h) | Aufwand in T-Shirt Sizes | Entspricht Personen- tagen | Entspricht Personen- monaten | Granularität | Anzuwenden in der Phase
512 | 1024 | XXL | 128 | 12.8 | Epics | Vorprojekt
256 | 512 | XXL | 64 | 6.4 | Epics | Vorprojekt
128 | 256 | XXL | 32 | 3.2 | Epics | Vorprojekt
64 | 128 | XL | 16 | 1.6 | Epics | Vorprojekt
32 | 64 | L | 8 | 0.8 | Epics / User Story | Vorprojekt/Sprint
16 | 32 | L | 4 | 0.4 | User Story | Sprint/Vorprojekt
8 | 16 | M | 2 | 0.2 | User Story | Sprint
4 | 8 | M | 1 | 0.1 | User Story | Sprint
2 | 4 | S | 0.5 | 0.05 | User Story | Sprint
1 | 2 | S | 0.25 | 0.025 | User Story | Sprint
0.5 | 1 | XS | 0.125 | 0.0125 | User Story | Sprint
0 | 0 | XS | 0 | 0 | User Story | Sprint
Ermittlung des Divisors für die Berechnung der Standardabweichung (Schätzformal nach McConnell)
Prozentsatz in den die tatsächlichen, einzelnen Ergebnisse innerhalb der geschätzen Bereiche fallen | Divisor für diese einzelne Schätzung
100 | 6
95 | 6
85 | 3.3
75 | 2.6
65 | 2.1
55 | 1.7
45 | 1.4
35 | 1
25 | 0.77
15 | 0.51
5 | 0.25
0 | 0.25
Ideale Umrechnungswerte Personen-Stunden / -Tage / -Monate / -Jahre
Umrechnung | Ideale Personenstunden
Stunden pro Personentag | 8
Stunden pro Monat | 160
Stunden pro Jahr | 1920
Wird für die Umrechnung des Gesamtaufwandes verwendet!