## Tabelle1
Sprint Review Protocol
Sprint No: |  | 5
Date & Time |  | 12.1.2022 16:56
Group Number |  | 14
Participant 1 |  | Brandenburg Jonas
Participant 2 |  | Dohnalek Raphael
Participant 3 |  | Duskanich Markus
Participant 4 |  | Duskanich Michael
Participant 5 |  | Meindl Tobias
Mentor |  | Eckkrammer Florian
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
509 | User can use File Menubar Menu | 4 | 3.9489 | -0.051111 | 1
510 | User can use Edit Menubar Menu | 4 | 2.3333 | 1.6667 | 1
511 | User can use View Menubar Menu | 2 | 2.3333 | -0.33333 | 1
532 | User can Toggle Datapanel | 1 | 0.6725 | 0.3275 | 1
585 | User can Toggle Simulation Diagram | 2 | 0.6725 | 1.3275 | 1
582 | User can Toggle Graph Editor | 2 | 0.6725 | 1.3275 | 1
533 | User can Resize Datapanel | 4 | 4.6821 | -0.68213 |  | 1 | Needs some minor code cleanup, but is overall functional
586 | User can Resize Simulation Diagram | 4 | 4.6821 | -0.68213 |  | 1 | Needs some minor code cleanup, but is overall functional
583 | User can Resize Graph Editor | 4 | 4.6821 | -0.68213 |  | 1 | Needs some minor code cleanup, but is overall functional
595 | Developer wants to have a basic graph database they can access | 10 | 10.25 | -0.25 | 1 |  | Needs some minor code cleanup, but is overall functional
611 | User wants to login | 0 | 0 | 0 |  | 1 | Needed rediscussion with Mentor, will be split up
|  |  |  | 2.2183 | 7 | 4
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol