## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 29.03.2022 14:51
Group Number |  | 14
Participant 1 |  | Brandenburg Jonas
Participant 2 |  | Dohnalek Raphael
Participant 3 |  | Duskanich Markus
Participant 4 |  | Duskanich Michael
Participant 5 |  | Meindl Tobias
Mentor |  | Eckkrammer Florian
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
650 | User wants to create project (backend) | 4 | 5 | 1 | 1
513 | User wants to create Network (backend) | 4 | 5 | -1 | 1
520 | User wants to change Network Name | 1 | 4 | -3 | 1
597 | User wants to access / change settings | 10 | 8 | 2 | 1
598 | User wants to undo / redo | 6 | 4 | 2 | 1
682 | User wants to create and manage instance>project>network hierarchy | 10 | 28 | -18 | 1
683 | User wants to save/load network structure on server backend | 16 | 16 | 0 | 1
610 | User can use common hotkeys | 6 | 6 | 0 | 1
666 | Developer wants to have prototype for instance>project>network hierarchy | 10 | 8 | 2 | 1
0
0
|  |  |  | -15 | 9 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol