## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 03.05.2022 00:53
Group Number |  | 14
Participant 1 |  | Brandenburg Jonas
Participant 2 |  | Dohnalek Raphael
Participant 3 |  | Duskanich Markus
Participant 4 |  | Duskanich Michael
Participant 5 |  | Meindl Tobias
Mentor |  | Eckkrammer Florian
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
698 | Change Ids from Neo4J to Guids | 2.25 | 2.25 | 0 | 1
699 | Add Update Network Structure | 5.5 | 5.5 | 0 | 1
641 | User wants to simulate the network | 4 | 3.25 | 0.75
682 | User wants to create and manage instance>project>network hierarchy | 10 | 5 | 5 | 1
0
0
0
0
0
0
0
|  |  |  | 5.75 | 3 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol