## Tabelle1
Sprint Review Protocol
Sprint No: |  | 4
Date & Time |  | 17.05.2022 00:53
Group Number |  | 14
Participant 1 |  | Brandenburg Jonas
Participant 2 |  | Dohnalek Raphael
Participant 3 |  | Duskanich Markus
Participant 4 |  | Duskanich Michael
Participant 5 |  | Meindl Tobias
Mentor |  | Eckkrammer Florian
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
682 | User wants to have Instance>Project>Network hierarchy | 10 | 78 | 68 | 1 |  | We restructered our frontend to support redux like stores, and updated it to use Guid instead of id's over the course of this story
0
0
0
0
0
0
0
0
0
0
|  |  |  | 68 | 1 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol